## Sheet1
EXAMPLE - Project Support Worksheet
Project Name: |  |  | Banner Flats
Sponsor Requesting NRCS Assistance: |  |  | SWCD
Time period for which assistance is requested: |  |  | FY15 and FY16
Counties in which project activities are planned: |  |  | Cass, Audubon, Guthrie
Sponsor signature: | [7 empty] | Date:
Estimated Support and Assistance
ASTC(FO) intial below to indicate support
| Office Space for _ 1 _ partner employees |  |  |  |  | 100 |  |  | _____ ASTC(FO)
| (number) |  |  |  |  | (Total square feet requested)
| Computer & access for _1__ partner employees | [7 empty] | _____ ASTC(FO)
(number)
| Vehicle access for _1__ partner employees | [7 empty] | _____ ASTC(FO)
(number)
| NRCS Technical Assistance for Conservation Planning |  |  |  |  | 15 |  |  | _____ ASTC(FO)
(Number of plans)
| NRCS Techncial Assistance for Practice Implementation (see back) General Description: |  |  |  |  | 25 |  |  | _____ ASTC(FO)
| 19 terraces and 6 GSS |  |  |  |  | (Number of projects)
Estimated project support and assistance provided by partners
| Financial Assistance (FA) to Construct Conservation Practices |  |  |  |  | 90000 |  | This item paid by partner
| Technical Assistance (TA) provided through Partner Employee |  |  |  |  | 35000 |  | This item paid by partner
(IA Instruction 330 – 381 Second Edition – August 2016) Page 1 of 2
EXAMPLE - Project Support Worksheet
Summary of TA Required to Complete Project
Practice Implementation | Planned Quantity | NRCS Engr. Staff Time |  |  | NRCS Field Office Staff Time |  |  | Partner Staff Time
|  | Implementation - Step 8 |  |  | Implementation - Step 8 |  |  | Implementation - Step 8
|  | layout | design | inspection | layout | design | inspection | layout | design | inspection
|  | survey | plans | check out | survey | plans | check out | survey | plans | check out
412 Waterway, acres
600 Terrace, feet | 50000 |  |  |  | 30 | 20 | 12 | 60 | 80 | 40
606 Subsurface Drain, feet | 75000 |  |  |  | 10 | 10 | 8 | 30 | 40 | 20
620 Underground Outlet, feet
638 WASCOB, each
410 Grade Stab, each | 6 | 56 | 150 | 240
378 Pond, each
313 Waste Storage Structure, each
605 Denitrifying Bioreactors
739 Vegetated Subsurface Drain Outlet
| Total Hours | 56 | 150 | 240 | 40 | 30 | 20 | 90 | 120 | 60
Recommendation:
| District Conservationist |  |  |  |  | Date
Review and Concurrance:
| Assistant State Conservationist for Field Operations |  |  |  |  | Date
Approval:
| State Conservationist |  |  |  |  | Date
(IA Instruction 330 – 381 Second Edition – August 2016) Page 2 of 2