Fiscal Year 2024 Timeline Targets for WREP: Entering into New Agreements and Obligations

| ACEP FY 2024 New Enrollment Actions | Date | Notes |
| --- | --- | --- |
| States will publish availability of funds for WREP along with notice of request for proposal. | By June 14, 2024 | Items needed for this are attached to this bulletin. |
| Partner proposal workshop. | June 20, 2024, 2 to 4pm EDT | Opportunity to discuss FY 2024 program changes and ranking criteria with NRCS national program managers. |
| Proposal deadline for partner submissions to states. | August 16, 2024 | Partners submit completed proposals to states with courtesy NRCS.ProgramAgreements@usda.gov for consideration and ranking. |
| States will submit eligible proposals to NHQ EPD for consideration. | August 23, 2024 | States will work with partners to review and finalize budget. Upload proposal submission to the WREP FY 2025 folder in the EPD SharePoint and notify WREP program manager by email. |
| National Review Board ranks and prioritizes proposals and makes recommendation to the Chief. | September 6, 2024 | Evaluate budgetary impacts. Develop recommendations for the Chief. |
| Chief selects proposals. | Target: September 27, 2024 |  |
| States notify partners of proposals selected for funding. | Target: October 4, 2024 | States communicate with partners to ensure awarded proposal amount is sufficient to implement proposal. |
| Announce approved WREP proposals for FY 2025 | Target October 2024 | With coordination across departments, public announcements are made through a news release. Send letters of selection to approved partners and letters of non-selection to any who didn’t rank high enough to be funded this year. |
| States execute WREP Agreements. | November 2024 (30 days after announcement) | EPD provides WREP agreement for execution. |
| States provide a copy of executed agreement to EPD | December 2024 (within 15 days of execution) | EPD enters NEST data to create active agreement, notifies state that the agreement is approved, and records obligation in FMMI. |
| Distribution of FY 2025 WREP funding | January 2025 | National ACEP-WRE manager notifies states when funds have been allocated in FMMI. |