Attachment B
Fiscal Year 2024 Timeline Targets for WREP: Entering into New Agreements and Obligations
	ACEP FY 2024 New Enrollment Actions
	Date
	Notes

	States will publish availability of funds for WREP along with notice of request for proposal.
	By June 14, 2024
	Items needed for this are attached to this bulletin.

	Partner proposal workshop.
	June 20, 2024, 
2 to 4pm EDT
	Opportunity to discuss FY 2024 program changes and ranking criteria with NRCS national program managers.

	Proposal deadline for partner submissions to states.
	August 16, 2024
	Partners submit completed proposals to states with courtesy NRCS.ProgramAgreements@usda.gov for consideration and ranking.

	States will submit eligible proposals to NHQ EPD for consideration.
	August 23, 2024
	States will work with partners to review and finalize budget. Upload proposal submission to the WREP FY 2025 folder in the EPD SharePoint and notify WREP program manager by email.

	National Review Board ranks and prioritizes proposals and makes recommendation to the Chief.
	September 6, 2024
	Evaluate budgetary impacts. Develop recommendations for the Chief.

	Chief selects proposals.  
	Target:  September 27, 2024
	

	States notify partners of proposals selected for funding.
	Target: October 4, 2024
	States communicate with partners to ensure awarded proposal amount is sufficient to implement proposal. 

	Announce approved WREP proposals for FY 2025
	Target October  2024
	With coordination across departments, public announcements are made through a news release. 
Send letters of selection to approved partners and letters of non-selection to any who didn’t rank high enough to be funded this year.

	States execute WREP Agreements.
	November 2024 (30 days after announcement)
	EPD provides WREP agreement for execution.

	States provide a copy of executed agreement to EPD 
	December 2024 (within 15 days of  execution)
	EPD enters NEST data to create active agreement, notifies state that the agreement is approved, and records obligation in FMMI.

	Distribution of FY 2025 WREP funding 
	January 2025
	National ACEP-WRE manager notifies states when funds have been allocated in FMMI.
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